## STAR Evaluation Framework
Document | Project Phase | Evaluation Category | Evaluation Metrics | Evaluation Pointers
SOW (Statement of Work) | Project Initiation | Must Have | Agreement, Effective Date & Contract Reference Clarity | Verify whether effective date, governing agreement, contract references, amendment clauses, and legal applicability are clearly defined
SOW (Statement of Work) | Project Initiation | Must Have | Project Objectives, Services & Scope Definition | Verify whether project objectives, operational expectations, services to be provided, and business scope are clearly documented
SOW (Statement of Work) | Project Initiation | Must Have | Services to be Provided by Service Provider | Verify whether all operational, reporting, support, enhancement, refresh, QC, validation, and stakeholder support activities are clearly listed
SOW (Statement of Work) | Project Initiation | Must Have | In-Scope vs Out-of-Scope Coverage | Verify whether supported activities, exclusions, enhancement limitations, and operational boundaries are clearly separated
SOW (Statement of Work) | Project Initiation | Must Have | Deliverables & Operational Expectations | Verify whether deliverables such as refreshed reports, extracts, QC checklists, validations, insights, and operational outputs are clearly defined
SOW (Statement of Work) | Project Initiation | Must Have | Timeline, Milestones & Duration Management | Verify whether project duration, completion dates, milestone expectations, refresh schedules, and operational timelines are documented
SOW (Statement of Work) | Project Initiation | Must Have | Service Provider Contacts & Governance Structure | Verify whether project leaders, delivery managers, escalation contacts, invoicing contacts, and governance ownership are documented
SOW (Statement of Work) | Project Initiation | Must Have | Team Structure & Resource Allocation | Verify whether delivery hierarchy, team structure, operational ownership, and resource responsibilities are clearly defined
SOW (Statement of Work) | Project Initiation | Must Have | Roles, Responsibilities & Operational Ownership | Verify whether client/vendor responsibilities, operational ownership, dependency handling, and support responsibilities are clearly assigned
SOW (Statement of Work) | Project Initiation | Must Have | Compensation, Cost, Pricing & Billing Rate Structure | Verify whether pricing structure, blended billing rates, enhancement rates, compensation limits, pass-through costs, and commercial expectations are clearly documented
SOW (Statement of Work) | Project Initiation | Must Have | Invoicing Schedule & Payment Milestones | Verify whether invoicing frequency, payment milestones, invoice conditions, billing cycles, and milestone-based payment schedules are documented
SOW (Statement of Work) | Project Initiation | Must Have | Travel, Reimbursement & Pass-through Cost Governance | Verify whether travel clauses, reimbursement handling, pass-through approval conditions, and additional cost governance are documented
SOW (Statement of Work) | Project Initiation | Must Have | Change Management & Enhancement Governance | Verify whether change requests, enhancement limits, additional billing conditions, and scope revision handling are documented
SOW (Statement of Work) | Project Initiation | Must Have | Acceptance Criteria & Sign-off Readiness | Verify whether milestone completion criteria, acceptance expectations, approval workflows, and sign-off conditions are documented
SOW (Statement of Work) | Project Initiation | Must Have | Operational Support, SLA & Service Expectations | Verify whether dashboard refresh support, discrepancy handling, stakeholder query support, QC expectations, and operational SLAs are clearly defined
SOW (Statement of Work) | Project Initiation | Must Have | Risk, Dependency & Assumption Management | Verify whether assumptions, operational constraints, dependency handling, and risk conditions are documented
SOW (Statement of Work) | Project Initiation | Good to Have | Strategic Context & Business Alignment | Verify whether strategic objectives, business alignment, and transformation goals are documented
SOW (Statement of Work) | Project Initiation | Good to Have | Versioning, Documentation & Audit Governance | Verify whether revision logs, version tracking, documentation governance, and audit traceability are maintained
SOW (Statement of Work) | Project Initiation | Good to Have | Scope Visualization & Workflow Representation | Verify whether workflow diagrams, operational flows, and scope representations are visually documented
SOW (Statement of Work) | Project Initiation | Good to Have | Future Enhancement & Scalability Planning | Verify whether future enhancements, scalability expectations, and operational growth planning are documented
SOW (Statement of Work) | Project Initiation | Good to Have | Compliance, Confidentiality & Legal Governance | Verify whether confidentiality clauses, compliance obligations, IP ownership, and legal governance expectations are documented
Pricing Tool / Finance Document (Cost Estimator/WLBU) | Project Initiation | Must Have | Current Template & Rate Card | Verify whether the estimate uses the current pricing template and the rate card version named on the rate card tab
Pricing Tool / Finance Document (Cost Estimator/WLBU) | Project Initiation | Must Have | Project Dates & Duration | Verify whether project name, start date and end date are filled in and agree with the SOW
Pricing Tool / Finance Document (Cost Estimator/WLBU) | Project Initiation | Must Have | Resource Plan Completeness | Verify whether every resource line carries a location, position and domain, since that combination drives the rate lookup
Pricing Tool / Finance Document (Cost Estimator/WLBU) | Project Initiation | Must Have | Week-wise Effort Phasing | Verify whether hours are phased week by week, with nothing planned outside the project start and end dates
Pricing Tool / Finance Document (Cost Estimator/WLBU) | Project Initiation | Must Have | Rate Card Integrity | Verify whether billing and cost rates come from the locked rate card, with no manual overrides
Pricing Tool / Finance Document (Cost Estimator/WLBU) | Project Initiation | Must Have | Gross Margin Threshold | Verify whether the proposed gross margin clears 40 percent, and if not, whether a written commercial justification exists
Pricing Tool / Finance Document (Cost Estimator/WLBU) | Project Initiation | Must Have | Discount Threshold | Verify whether the discount stays within 10 percent, and if it does not, whether the prior Partner approval is on file
Pricing Tool / Finance Document (Cost Estimator/WLBU) | Project Initiation | Must Have | High-Value Approval Routing | Verify whether high-value deals with margin below the benchmark went for pricing review and Partner approval before the proposal left
Pricing Tool / Finance Document (Cost Estimator/WLBU) | Project Initiation | Must Have | Blended Rate Sanity Check | Verify whether the blended billing rate is calculated correctly and looks sensible against comparable engagements
Pricing Tool / Finance Document (Cost Estimator/WLBU) | Project Initiation | Good to Have | Onshore-Offshore Mix | Verify whether the offshore share and the seniority pyramid are realistic for the work being priced
Pricing Tool / Finance Document (Cost Estimator/WLBU) | Project Initiation | Good to Have | SOW Commercial Alignment | Verify whether duration, resourcing, discount and estimate all match the executed SOW

## DEx Evaluation Framework
Document | Project Phase | Evaluation Category | Evaluation Metrics | Evaluation Pointers
Functional Requirement Document (FRD/FSD/FRS) | Requirement Gathering | Must Have | Functional Requirement Completeness & Logic | Verify workflows, calculations, validations, transformations, dependencies, and implementation behavior are completely defined
Functional Requirement Document (FRD/FSD/FRS) | Requirement Gathering | Must Have | Data Source, Integration & Processing Requirements | Verify source systems, ingestion methods, APIs, refresh logic, integration behavior, and processing expectations
Functional Requirement Document (FRD/FSD/FRS) | Requirement Gathering | Must Have | Reporting & Analytics Requirements | Verify KPIs, dashboards, filters, drilldowns, exports, visualizations, aggregation logic, and reporting behavior
Functional Requirement Document (FRD/FSD/FRS) | Requirement Gathering | Must Have | Security, Access & Non-Functional Requirements | Verify RBAC, user visibility, scalability, performance, SLAs, latency, and operational expectations
Functional Requirement Document (FRD/FSD/FRS) | Requirement Gathering | Must Have | Validation, Reconciliation & Exception Handling | Verify DQ rules, reconciliation logic, duplicate handling, retry mechanisms, logging, and exception handling
Functional Requirement Document (FRD/FSD/FRS) | Requirement Gathering | Must Have | Technical Implementation Readiness | Assess whether engineering and QA teams can directly begin development/testing without ambiguity
Functional Requirement Document (FRD/FSD/FRS) | Requirement Gathering | Must Have | Dependency, Assumptions & Constraints Management | Verify upstream/downstream dependencies, assumptions, sequencing logic, and technical constraints
Functional Requirement Document (FRD/FSD/FRS) | Requirement Gathering | Must Have | Mockups, Wireframes & Process Flow Representation | Verify inclusion of visual flows, architecture diagrams, wireframes, or process representations
Functional Requirement Document (FRD/FSD/FRS) | Requirement Gathering | Must Have | Requirement Traceability | Verify whether each specification points back to the business or functional requirement it satisfies
Functional Requirement Document (FRD/FSD/FRS) | Requirement Gathering | Must Have | System Behaviour Defined | Verify whether the document says what the system does when a user takes an action
Functional Requirement Document (FRD/FSD/FRS) | Requirement Gathering | Must Have | Field-level Specification | Verify whether inputs and outputs are named at field level with types, formats and mandatory flags
Functional Requirement Document (FRD/FSD/FRS) | Requirement Gathering | Must Have | Calculation Logic | Verify whether every calculation and derivation is written out precisely enough that two developers would build it identically
Functional Requirement Document (FRD/FSD/FRS) | Requirement Gathering | Must Have | Volume & Retention | Verify whether expected volumes, the historical load period and retention requirements are stated
Functional Requirement Document (FRD/FSD/FRS) | Requirement Gathering | Must Have | Process Flow | Verify whether end-to-end process flows are documented with their sequence and decision branches
Functional Requirement Document (FRD/FSD/FRS) | Requirement Gathering | Good to Have | Business Alignment & User Context | Verify alignment with business objectives, user expectations, and operational use cases
Functional Requirement Document (FRD/FSD/FRS) | Requirement Gathering | Good to Have | Documentation, Glossary & Change Governance | Verify terminology consistency, version tracking, glossary definitions, and documentation standards
Functional Requirement Document (FRD/FSD/FRS) | Requirement Gathering | Good to Have | Edge Case Coverage | Check whether nulls, boundary conditions and negative scenarios are described
Business Rule Document (BRD) | Requirement Gathering | Must Have | Business Objectives, KPIs & Expected Outcomes | Verify business goals, KPIs, expected outcomes, business problems, and success criteria are clearly defined
Business Rule Document (BRD) | Requirement Gathering | Must Have | Scope & Business Requirements Coverage | Verify in-scope/out-of-scope processes, reporting expectations, operational needs, and business requirements are documented
Business Rule Document (BRD) | Requirement Gathering | Must Have | Business Rules, Metrics & Data Expectations | Verify business rules, calculations, derivations, granularity expectations, and reporting measures are documented
Business Rule Document (BRD) | Requirement Gathering | Must Have | Business Data Domain & Readiness | Verify subject areas, entities, reporting expectations, and analytical requirements are identified
Business Rule Document (BRD) | Requirement Gathering | Must Have | Stakeholder, Governance & Acceptance Readiness | Verify ownership, SMEs, approvers, governance expectations, and business acceptance criteria are documented
Business Rule Document (BRD) | Requirement Gathering | Good to Have | Business Value Mapping & Future Enhancements | Verify ROI, operational benefits, roadmap items, and future-state expectations are documented
Business Rule Document (BRD) | Requirement Gathering | Good to Have | Rule Categorization & Business Organization | Verify business rules are logically grouped by business function/domain/module
Business Rule Document (BRD) | Requirement Gathering | Good to Have | Historical, Compliance & Governance Expectations | Verify retention policies, compliance requirements, governance standards, and audit expectations
Business Rule Document (BRD) | Requirement Gathering | Good to Have | High-Level Data & Analytical Structure Readiness | Verify dimensions, hierarchies, data domains, and high-level source/target expectations are identified
Business Rule Document (BRD) | Requirement Gathering | Good to Have | Documentation, Assumptions & Change Governance | Verify assumptions, dependencies, terminology consistency, versioning, and documentation standards
SIT (System Integration Testing) Document | Testing | Must Have | Test Case Coverage | Verify whether all relevant test cases are covered across data validation, UI/UX, functional, security and access testing, with scenarios matched to the project type: for reporting or dashboarding projects, KPIs, reports, dashboards, charts, filters and modules; for data warehouse projects, medallion layer-wise tables, column business rules, aggregated versus source layers, reporting or analytical layer versus source, data standardisation and data type checks, constraint checks and any use case specific to the requirements; for report or dashboard to data warehouse projects, frontend to backend value match; for custom applications, UI/UX, functionality and frontend to backend data validation
SIT (System Integration Testing) Document | Testing | Must Have | SQL Query Validation | Verify whether backend SQL/datamart queries are properly documented and executable
SIT (System Integration Testing) Document | Testing | Must Have | Data Match Validation | Verify whether frontend and backend values match correctly
SIT (System Integration Testing) Document | Testing | Must Have | Pass/Fail Status Tracking | Verify whether each test case includes pass/fail indicators
SIT (System Integration Testing) Document | Testing | Must Have | Exception Handling Validation | Verify whether exceptions and mismatches are captured properly
SIT (System Integration Testing) Document | Testing | Must Have | Test Data Validation | Verify whether test data ranges, products, and dimensions are properly validated
SIT (System Integration Testing) Document | Testing | Must Have | Aggregation Validation | Verify whether aggregation logic like KPI, monthly, regional summaries, and charts are validated
SIT (System Integration Testing) Document | Testing | Must Have | Report Visualization Validation | Verify whether charts, visuals, and dashboard outputs are validated correctly
SIT (System Integration Testing) Document | Testing | Must Have | Comments & Fix Tracking | Verify whether comments, fixes required, and issue tracking fields are maintained
SIT (System Integration Testing) Document | Testing | Must Have | Time Period Validation | Verify whether date ranges and reporting periods are validated correctly
SIT (System Integration Testing) Document | Testing | Must Have | End-to-End Reconciliation Readiness | Verify whether source-to-report reconciliation is traceable and testable
SIT (System Integration Testing) Document | Testing | Good to Have | Module-wise Test Categorization | Check whether test cases are grouped by dashboard/module/KPI
SIT (System Integration Testing) Document | Testing | Good to Have | Automated Validation Readiness | Check whether validation logic supports automation or reusable scripts
SIT (System Integration Testing) Document | Testing | Good to Have | Query Optimization Checks | Check whether validation queries are optimized and reusable
SIT (System Integration Testing) Document | Testing | Good to Have | Negative Testing Coverage | Check whether invalid or edge-case filter scenarios are tested
SIT (System Integration Testing) Document | Testing | Good to Have | Tolerance Threshold Definition | Check whether acceptable variance thresholds are defined
SIT (System Integration Testing) Document | Testing | Good to Have | Defect Severity Classification | Check whether defects are categorized by severity/priority
SIT (System Integration Testing) Document | Testing | Good to Have | Root Cause Analysis Tracking | Check whether RCA details are captured for failed scenarios
SIT (System Integration Testing) Document | Testing | Good to Have | Historical Data Validation | Check whether historical periods and trend validations are tested
SIT (System Integration Testing) Document | Testing | Good to Have | Drilldown Validation | Check whether drilldowns and hierarchical reporting are tested
SIT (System Integration Testing) Document | Testing | Good to Have | UI/UX Consistency Validation | Check whether dashboard formatting and usability are validated
SIT (System Integration Testing) Document | Testing | Good to Have | Defect Lifecycle Tracking | Check whether defect resolution lifecycle is tracked
SIT (System Integration Testing) Document | Testing | Good to Have | Refresh & Scheduling Validation | Check whether report refresh timing and scheduling are validated
SIT (System Integration Testing) Document | Testing | Good to Have | Audit & Execution Traceability | Check whether tester details, timestamps, and execution tracking are maintained
Universal Document Standards (Applies to All Documents) | All Phases | Must Have | Standard Template Usage | Verify whether the document sits on the current ProcDNA template rather than a format someone built themselves
Universal Document Standards (Applies to All Documents) | All Phases | Must Have | File Naming Compliance | Verify whether the file name carries the date, project, document title, version and author initials
Universal Document Standards (Applies to All Documents) | All Phases | Must Have | Author & Approver Named | Verify whether the document names who wrote it, who reviewed it and who approved it
Universal Document Standards (Applies to All Documents) | All Phases | Must Have | Single Live Version | Verify whether only one live copy sits in the working folder, with superseded versions moved to archive
Universal Document Standards (Applies to All Documents) | All Phases | Good to Have | Terminology Consistency | Verify whether the same thing is called the same name throughout, with terms defined where they first appear
e.g. Refer to HCP as either HCP, doctor, MD, prescriber or physician throughout all the documents.
Universal Document Standards (Applies to All Documents) | All Phases | Good to Have | Client Repository Sync | Check whether documents owed to the client also sit in the client folder and match the internal copy
Universal Document Standards (Applies to All Documents) | All Phases | Good to Have | Access & Confidentiality | Check whether access is restricted to the right people and any sensitivity marking is applied
Universal Document Standards (Applies to All Documents) | All Phases | Good to Have | Evidence Attached | Check whether claims of completion are backed by evidence such as screenshots, logs or query output
Project Charter / Project Plan / Schedule / Scope | Project Initiation | Must Have | Business Case & Objectives | Verify whether the charter states the business problem being solved and what success looks like in measurable terms
Project Charter / Project Plan / Schedule / Scope | Project Initiation | Must Have | Scope Boundaries | Verify whether the charter says what is in scope and, just as plainly, what is not
Project Charter / Project Plan / Schedule / Scope | Project Initiation | Must Have | Deliverables & Milestones | Verify whether the main deliverables are listed with phase milestones, client review points, approval gates and target dates
Project Charter / Project Plan / Schedule / Scope | Project Initiation | Must Have | Sponsor & Governance Structure | Verify whether the sponsor, key stakeholders and the forum that makes decisions are all named
Project Charter / Project Plan / Schedule / Scope | Project Initiation | Must Have | Team Structure & Allocation | Verify whether the charter names the team, their roles and how much of their time the project gets
Project Charter / Project Plan / Schedule / Scope | Project Initiation | Must Have | Budget & Effort Estimate | Verify whether the charter carries a budget and effort estimate
Project Charter / Project Plan / Schedule / Scope | Project Initiation | Must Have | Risks & Assumptions | Verify whether the known risks, assumptions and constraints are written down with an owner against each
Project Charter / Project Plan / Schedule / Scope | Project Initiation | Must Have | Success Criteria | Verify whether the charter defines measurable success criteria and how the project will be accepted as complete
Project Charter / Project Plan / Schedule / Scope | Project Initiation | Must Have | Delivery Methodology | Verify whether the charter states the delivery methodology and the working rhythm that goes with it
Project Charter / Project Plan / Schedule / Scope | Project Initiation | Must Have | SOW Alignment | Verify whether the charter's scope, timeline and deliverables match what the SOW actually commits to
Project Charter / Project Plan / Schedule / Scope | Project Initiation | Must Have | Charter Authorization | Verify whether someone with the authority to start the project has signed the charter, with a date
Project Charter / Project Plan / Schedule / Scope | Project Initiation | Must Have | Task-level Breakdown | Verify whether the work is broken into tasks small enough to track meaningfully
Project Charter / Project Plan / Schedule / Scope | Project Initiation | Must Have | Approved Baseline | Verify whether an approved baseline exists as the reference against which slippage is measured
Project Charter / Project Plan / Schedule / Scope | Project Initiation | Must Have | Task Ownership | Verify whether each task names an individual rather than a team
Project Charter / Project Plan / Schedule / Scope | Project Initiation | Must Have | Dependencies & Critical Path | Verify whether task dependencies, sequencing and the critical path are identified
Project Charter / Project Plan / Schedule / Scope | Project Initiation | Must Have | Plan vs Actual | Verify whether actual progress is tracked against baseline so variance and slippage are visible
Project Charter / Project Plan / Schedule / Scope | Project Initiation | Must Have | Buffer & Timeline Realism | Verify whether the plan leaves room for review cycles and defect fixing rather than assuming everything lands first time
Project Charter / Project Plan / Schedule / Scope | Project Initiation | Good to Have | Solution Approach | Check whether the charter outlines how the solution will be built and on what platform
Project Charter / Project Plan / Schedule / Scope | Project Initiation | Good to Have | Reporting Cadence | Check whether the charter sets out reporting cadence, governance meetings and how issues escalate
Project Charter / Project Plan / Schedule / Scope | Project Initiation | Good to Have | Leave & Holiday Overlay | Check whether team leave and holiday calendars are reflected in the schedule
RAID Log (Risks, Assumptions, Issues, Dependencies) | Project Management | Must Have | Full RAID Coverage | Verify whether risks, assumptions, issues and dependencies are all present and sitting in the right category
RAID Log (Risks, Assumptions, Issues, Dependencies) | Project Management | Must Have | Entry ID & Description | Verify whether each entry has an ID and a description specific enough to act on
RAID Log (Risks, Assumptions, Issues, Dependencies) | Project Management | Must Have | Impact & Priority Rating | Verify whether each risk carries an impact rating and the priority that follows from them
RAID Log (Risks, Assumptions, Issues, Dependencies) | Project Management | Must Have | Mitigation & Contingency | Verify whether each risk has both a mitigation to stop it happening and a contingency for if it does
RAID Log (Risks, Assumptions, Issues, Dependencies) | Project Management | Must Have | One Named Owner per Item | Verify whether every item names one person as owner rather than a team
RAID Log (Risks, Assumptions, Issues, Dependencies) | Project Management | Must Have | Dates & Status | Verify whether raised date, due date, current status are all maintained
RAID Log (Risks, Assumptions, Issues, Dependencies) | Project Management | Must Have | Issue Escalation Path | Verify whether open issues show an escalation trigger, a contact and the action being taken
RAID Log (Risks, Assumptions, Issues, Dependencies) | Project Management | Must Have | Dependency Impact | Verify whether dependencies name the party being waited on and the timeline impact if they slip
RAID Log (Risks, Assumptions, Issues, Dependencies) | Project Management | Must Have | Log Currency | Verify whether the log is genuinely live, with no items sitting long past their due date
RAID Log (Risks, Assumptions, Issues, Dependencies) | Project Management | Good to Have | Workstream Tagging | Check whether items are tagged by workstream or phase so they can be filtered and reported
Kick off Deck | Project Management | Must Have | Project Overview & Objectives | Verify whether the deck sets out the project purpose, objectives and expected outcomes for the audience
Kick off Deck | Project Management | Must Have | Scope Walkthrough | Verify whether in-scope and out-of-scope items were presented so both sides leave with the same understanding
Kick off Deck | Project Management | Must Have | Delivery Approach & Timeline | Verify whether the delivery methodology, phases, milestones and key dates were presented
Kick off Deck | Project Management | Must Have | Team Introductions & Contacts | Verify whether delivery and client team members are introduced with names, roles and contact points
Kick off Deck | Project Management | Must Have | Tools, Access & Environments | Verify whether the tools, repositories and access the project will use are covered, along with who arranges what
Kick off Deck | Project Management | Must Have | Assumptions, Risks & Dependencies Raised | Verify whether known assumptions, early risks and client-side dependencies were flagged at kick-off
Kick off Deck | Project Management | Must Have | Deck Circulated & Acknowledged | Verify whether the deck was shared after the session and acknowledged by the client
Kick off Deck | Project Management | Must Have | Activity Coverage | Verify whether activities are listed at a level granular enough for someone to be held to them
Kick off Deck | Project Management | Must Have | Role Definitions & Legend | Verify whether roles are spelled out with a RACI legend and real names attached where possible
Kick off Deck | Project Management | Must Have | RACI like component | Define dependencies, owners, POCs to assign RACI for both Business team from the client side, IT Team from the client side, ProcDNA team/s and/or other vendors
Kick off Deck | Project Management | Must Have | Function-wise Coverage | Verify whether the RACI covers every function including data, engineering, BI, QA, infrastructure and security
Kick off Deck | Project Management | Must Have | Internal Role Definition | Verify whether internal roles, reporting lines and individual ownership are defined
Kick off Deck | Project Management | Must Have | Handoff Ownership | Verify whether each handoff says who passes the work, who receives it and who accepts it
Kick off Deck | Project Management | Must Have | Decision Rights | Verify whether decision rights for scope, design and release decisions are assigned to named roles
Kick off Deck | Project Management | Must Have | Escalation Matrix | Verify whether escalation levels, contacts and expected response times are documented
Kick off Deck | Project Management | Must Have | Engagement Model | Verify whether recurring communication is listed with the purpose it serves with audience, frequency and channel
Kick off Deck | Project Management | Must Have | Governance Forums | Verify whether status reporting and the governance or steering forums are defined with their cadence
Kick off Deck | Project Management | Good to Have | Ways of Working | Check whether working hours, response expectations and the definition of done are covered
Kick off Deck | Project Management | Good to Have | Success Criteria | Check whether the agreed success criteria are restated so the team starts aligned
Kick off Deck | Project Management | Good to Have | Next Steps & Immediate Actions | Check whether the deck closes with immediate next steps carrying owners and dates
Kick off Deck | Project Management | Good to Have | Phase-wise Grouping | Check whether activities are grouped by phase or workstream so the matrix can be read easily
Kick off Deck | Project Management | Good to Have | Client Turnaround Times | Check whether client-side dependencies such as access, data and approvals carry agreed turnaround times
Kick off Deck | Project Management | Good to Have | Backup Owners | Check whether critical roles have a named backup so absence does not stop the work
Kick off Deck | Project Management | Good to Have | Overlap Hours | Check whether working hours, overlap windows and availability across geographies are addressed
Kick off Deck | Project Management | Good to Have | Meeting Ground Rules | Check whether ground rules on agendas, meeting notes and documentation are set out
Kick off Deck | Project Management | Good to Have | Plan Kept Current | Check whether the plan is refreshed when stakeholders or the meeting rhythm change
Change Control Register/Change Tracker | Project Management | Must Have | CR Identification | Verify whether each change carries an ID, who raised it, when, and a description that explains the business reason
Change Control Register/Change Tracker | Project Management | Must Have | Scope, Time & Cost Impact | Verify whether each change records its effect on scope, schedule, effort and budget in actual numbers
Change Control Register/Change Tracker | Project Management | Must Have | Downstream Impact Analysis | Verify whether the assessment covers what else the change touches, including data model, interfaces, reports and tests
Change Control Register/Change Tracker | Project Management | Must Have | Approval Decision Record | Verify whether the approver, the decision, the date and any conditions attached are all recorded
Change Control Register/Change Tracker | Project Management | Must Have | Implementation Ownership | Verify whether every approved change has an implementation owner, a priority, a target date and a status
Change Control Register/Change Tracker | Project Management | Must Have | Baseline Updated | Verify whether approved changes have flowed back into the scope, plan, requirement and design baselines
Change Control Register/Change Tracker | Project Management | Must Have | Rejected CRs Retained | Verify whether rejected and deferred requests are retained along with the reason for the decision
Stakeholder Register | Project Management | Must Have | Stakeholder Coverage | Verify whether internal, client and third-party stakeholders are all listed with name, role and organisation
Stakeholder Register | Project Management | Must Have | Influence & Interest Rating | Verify whether each stakeholder has an assessed level of influence and interest
Stakeholder Register | Project Management | Must Have | Engagement Approach | Verify whether each stakeholder is mapped to an engagement approach such as manage closely, keep satisfied or monitor
Stakeholder Register | Project Management | Must Have | Channel & Frequency | Verify whether the register records how often each stakeholder hears from the project and through which channel
Stakeholder Register | Project Management | Must Have | Expectations & Concerns | Verify whether the register captures what each stakeholder wants from the project and what worries them
Stakeholder Register | Project Management | Must Have | Approval Authority Mapped | Verify whether approvers, sign-off authorities and escalation contacts are identified
Stakeholder Register | Project Management | Good to Have | Attitude Tracking | Check whether current and target stakeholder attitudes are recorded along with how the gap will be closed
Stakeholder Register | Project Management | Good to Have | Engagement Actions | Check whether specific engagement actions are documented with owners and review dates
Stakeholder Register | Project Management | Good to Have | Register Kept Current | Check whether the register is refreshed when stakeholders change roles or leave
Action Log | Project Management | Must Have | Action Description | Verify whether each action has an ID and a description that states the outcome expected
Action Log | Project Management | Must Have | One Named Owner per Action | Verify whether every action names one owner
Action Log | Project Management | Must Have | Dates & Overdue Visibility | Verify whether raised and due dates are recorded and overdue items are visible
Action Log | Project Management | Must Have | Status Kept Current | Verify whether the status column reflects where each action actually stands
Action Log | Project Management | Must Have | Priority Classification | Verify whether actions carry a priority so critical items stand apart from routine follow-ups
Action Log | Project Management | Must Have | Source Traceability | Verify whether each action can be traced to the meeting, decision or escalation it came from
Action Log | Project Management | Must Have | Closure Comments | Verify whether closed actions record the closure date and what was actually done
Action Log | Project Management | Good to Have | Category Tagging | Check whether actions are tagged by type or workstream so they can be grouped
Action Log | Project Management | Good to Have | Carry-forward Escalation | Check whether actions that keep slipping are escalated rather than quietly re-dated
Action Log | Project Management | Good to Have | Open vs Closed Summary | Check whether a summary of open, in-progress and closed actions is available
Data Dictionary / KPI Glossary | Deployment | Must Have | Full Object Coverage | Verify whether every reporting table, view and column is documented
Data Dictionary / KPI Glossary | Deployment | Must Have | Technical Attributes | Verify whether data type, length, nullability and key designation are recorded per field
Data Dictionary / KPI Glossary | Deployment | Must Have | Field Business Definition | Verify whether each field has a plain-language business definition rather than a restatement of its name
Data Dictionary / KPI Glossary | Deployment | Must Have | Source & Lineage | Verify whether the originating source and derivation lineage are identified per field
Data Dictionary / KPI Glossary | Deployment | Must Have | Allowed Values | Verify whether valid value sets and code lists are documented
Data Dictionary / KPI Glossary | Deployment | Must Have | Grain & Relationships | Verify whether table grain, keys and relationships are described
Data Dictionary / KPI Glossary | Deployment | Must Have | Refresh Frequency | Verify whether refresh frequency and data currency are stated per object
Data Dictionary / KPI Glossary | Deployment | Must Have | Owners & Stewards | Verify whether business owner, data steward and technical owner are named
Data Dictionary / KPI Glossary | Deployment | Must Have | Full KPI Inventory | Verify whether every metric exposed in reporting appears in the glossary
Data Dictionary / KPI Glossary | Deployment | Must Have | KPI Business Definition | Verify whether each KPI has a definition a business user could understand unaided
Data Dictionary / KPI Glossary | Deployment | Must Have | Calculation Formula | Verify whether the exact formula is stated, including numerator, denominator and filters
Data Dictionary / KPI Glossary | Deployment | Must Have | Source Tables | Verify whether the source table and attributes behind each KPI are identified
Data Dictionary / KPI Glossary | Deployment | Must Have | Granularity & Slicing | Verify whether the granularity and the dimensions each KPI can be sliced by are documented
Data Dictionary / KPI Glossary | Deployment | Must Have | Time Period Definitions | Verify whether time definitions such as MTD, QTD, YTD and rolling periods are defined precisely
Data Dictionary / KPI Glossary | Deployment | Must Have | Inclusions & Exclusions | Verify whether the records counted and the records excluded from each KPI are stated
Data Dictionary / KPI Glossary | Deployment | Must Have | Matches the Built Measure | Verify whether the glossary definitions match the measure logic actually running in the reporting layer
Data Dictionary / KPI Glossary | Deployment | Good to Have | Sensitive Field Flagging | Check whether sensitive and personally identifiable fields are flagged with handling rules
Data Dictionary / KPI Glossary | Deployment | Good to Have | Definition Change Control | Check whether definition changes go through governance and are versioned
Data Dictionary / KPI Glossary | Deployment | Good to Have | Visual Guidance | Check whether the recommended visual type for each KPI is indicated
Data Dictionary / KPI Glossary | Deployment | Good to Have | KPI Owner | Check whether each KPI has a business owner and approver
Implementation Plan / Rollback Plan | Deployment | Must Have | Release Contents | Verify whether the components, versions and changes being deployed are itemised
Implementation Plan / Rollback Plan | Deployment | Must Have | Team & Availability | Verify whether the deployment team, contacts and their availability during the window are documented
Implementation Plan / Rollback Plan | Deployment | Must Have | Prerequisites & Approvals | Verify whether prerequisites, approvals and code freeze confirmation are captured
Implementation Plan / Rollback Plan | Deployment | Must Have | Execution Runbook | Verify whether steps are sequenced with owners, durations and verification points
Implementation Plan / Rollback Plan | Deployment | Must Have | Backup Taken & Verified | Verify whether backups were taken and verified before production was touched
Implementation Plan / Rollback Plan | Deployment | Must Have | Post-deployment Verification | Verify whether post-deployment checks and the criteria for restoring user access are defined
Implementation Plan / Rollback Plan | Deployment | Must Have | Go / No-Go Criteria | Verify whether go and no-go criteria, checkpoint timing and the decision authority are defined
Implementation Plan / Rollback Plan | Deployment | Must Have | Rollback Triggers | Verify whether the plan states precisely what conditions trigger a rollback
Implementation Plan / Rollback Plan | Deployment | Must Have | Rollback Steps | Verify whether rollback steps, sequence, owners and expected duration are documented
Implementation Plan / Rollback Plan | Deployment | Must Have | Post-rollback Verification | Verify whether post-rollback checks and data integrity confirmation are defined
Implementation Plan / Rollback Plan | Deployment | Must Have | Deployment Communications | Verify whether user notifications and status updates are planned with owners and timing
Implementation Plan / Rollback Plan | Deployment | Good to Have | Deployment Risks | Check whether risks specific to this release and their mitigations are documented
Implementation Plan / Rollback Plan | Deployment | Good to Have | Rollback Rehearsed | Check whether the rollback procedure was tested in a lower environment
Implementation Plan / Rollback Plan | Deployment | Good to Have | Post-implementation Review | Check whether a post-implementation review is planned to capture lessons
Support Runbook / SOP | Hypercare | Must Have | System & Support Scope | Verify whether the runbook describes the system, its components and what support does and does not cover
Support Runbook / SOP | Hypercare | Must Have | Job Inventory & Schedule | Verify whether every scheduled job is listed with its schedule, dependencies and expected duration
Support Runbook / SOP | Hypercare | Must Have | Operational Procedures | Verify whether routine procedures are written as steps someone could follow without prior knowledge
Support Runbook / SOP | Hypercare | Must Have | Failure Runbooks | Verify whether common failures carry diagnosis steps, resolution actions and post-fix validation
Support Runbook / SOP | Hypercare | Must Have | Restart & Reprocessing | Verify whether job restart, backfill and reprocessing procedures are documented with their safeguards
Support Runbook / SOP | Hypercare | Must Have | Health Checks & Thresholds | Verify whether monitoring points, thresholds and daily health checks are documented
Support Runbook / SOP | Hypercare | Must Have | Escalation Contacts | Verify whether escalation levels, named contacts and response expectations are documented
Support Runbook / SOP | Hypercare | Must Have | Access & Credentials | Verify whether required access and credential retrieval are documented without exposing the secrets themselves
Support Runbook / SOP | Hypercare | Must Have | Severity & Response Times | Verify whether incident severity definitions and their response and resolution times are defined
Support Runbook / SOP | Hypercare | Good to Have | Known Issues | Check whether recurring issues and their workarounds are catalogued
Support Runbook / SOP | Hypercare | Good to Have | Manual Intervention Control | Check whether manual interventions in production require documented approval and logging
Support Runbook / SOP | Hypercare | Good to Have | BCP & DR Procedure | Check whether failover, disaster recovery and business continuity procedures are documented or referenced
Support Runbook / SOP | Hypercare | Good to Have | Runbook Kept Current | Check whether the runbook is version-controlled and reviewed at a set cadence
Security & Compliance Assessment | All Phases | Must Have | Access Control Review | Verify whether authentication, role-based access, least privilege and periodic access review were assessed
Security & Compliance Assessment | All Phases | Must Have | Row-Level Security Tested | Verify whether row-level and object-level security were tested for isolation and cannot be bypassed
Security & Compliance Assessment | All Phases | Must Have | Sensitive Data Handling | Verify whether PII and sensitive fields are identified with masking or restriction controls
Security & Compliance Assessment | All Phases | Must Have | Encryption in Transit & at Rest | Verify whether encryption standards for data in transit and at rest are documented and confirmed in place
Security & Compliance Assessment | All Phases | Must Have | Secret & Credential Management | Verify whether credentials sit in an approved secret store with rotation, and nothing is hardcoded in code
Security & Compliance Assessment | All Phases | Must Have | Audit Logging & Traceability | Verify whether access logs, change logs and audit trails are enabled and retained per policy
Security & Compliance Assessment | All Phases | Must Have | Environment Segregation | Verify whether production and non-production are segregated and production data is restricted in lower environments
Security & Compliance Assessment | All Phases | Must Have | Policy Mapped to Controls | Verify whether applicable regulations and client policies are mapped to the controls actually implemented
Security & Compliance Assessment | All Phases | Must Have | Findings Risk-Rated | Verify whether each finding carries a risk rating and its business impact
Security & Compliance Assessment | All Phases | Must Have | Remediation Plan | Verify whether every finding has a remediation action, owner, target date and status
Security & Compliance Assessment | All Phases | Must Have | Security Signed Off | Verify whether security approval was obtained before production release
Security & Compliance Assessment | All Phases | Good to Have | Retention & Disposal | Check whether retention periods and secure disposal requirements are covered
Security & Compliance Assessment | All Phases | Good to Have | Vendor Access Risk | Check whether third-party components and vendor access risks were assessed
Security & Compliance Assessment | All Phases | Good to Have | Reassessment Schedule | Check whether a schedule for reassessing security is defined
Learning Log | Project Management | Must Have | Entry Detail & Clarity | Verify whether each entry says what happened, when, and who it affected in enough detail to be useful
Learning Log | Project Management | Must Have | Root Cause Analysis | Verify whether entries analyse why it happened rather than only what happened
Learning Log | Project Management | Must Have | Action Taken & Outcome | Verify whether the corrective action taken and its outcome are documented
Learning Log | Project Management | Must Have | Preventive Control Added | Verify whether each learning results in a preventive control added to a checklist, standard or runbook
Learning Log | Project Management | Must Have | Category & Phase | Verify whether entries are categorised by type and tagged to the phase they arose in
Learning Log | Project Management | Must Have | Owner & Follow-up | Verify whether an owner and the status of the follow-up action are recorded
Learning Log | Project Management | Must Have | Logged as It Happens | Verify whether learnings were logged close to the event rather than reconstructed at project close
Learning Log | Project Management | Good to Have | Impact Rating | Check whether the impact of each learning is rated
Learning Log | Project Management | Good to Have | Linked to Documents | Check whether entries reference the standard or checklist that was updated as a result
Learning Log | Project Management | Good to Have | Reviewed at Retros | Check whether the log is reviewed at retrospectives and reusable learnings shared more widely
Non-Functional Requirements (NFR) Document | Requirement Gathering | Must Have | NFR Category Coverage | Verify whether the document covers performance, availability, scalability, security, data quality, maintainability and compliance
Non-Functional Requirements (NFR) Document | Requirement Gathering | Must Have | Quantified Targets | Verify whether every NFR carries a number rather than a subjective description
Non-Functional Requirements (NFR) Document | Requirement Gathering | Must Have | Performance Targets | Verify whether batch windows, query response times, dashboard load times and refresh SLAs are quantified
Non-Functional Requirements (NFR) Document | Requirement Gathering | Must Have | Uptime & Recovery Objectives | Verify whether uptime targets, maintenance windows, RTO and RPO are defined
Non-Functional Requirements (NFR) Document | Requirement Gathering | Must Have | Volume & Growth Assumptions | Verify whether current volumes, projected growth and concurrent user load are stated
Non-Functional Requirements (NFR) Document | Requirement Gathering | Must Have | Security Requirements | Verify whether authentication, authorisation, row-level security, encryption and PII handling requirements are specified
Non-Functional Requirements (NFR) Document | Requirement Gathering | Must Have | Data Quality Thresholds | Verify whether accuracy, completeness, timeliness and reconciliation tolerances are quantified
Non-Functional Requirements (NFR) Document | Requirement Gathering | Must Have | Monitoring & Alerting | Verify whether logging, monitoring, alert thresholds and supportability requirements are specified
Non-Functional Requirements (NFR) Document | Requirement Gathering | Must Have | Backup & Restore | Verify whether backup frequency, restore procedure and archival requirements carry measurable targets
Non-Functional Requirements (NFR) Document | Requirement Gathering | Must Have | NFR Testability | Verify whether each NFR says how it will be tested, in which environment, and what counts as a pass
Non-Functional Requirements (NFR) Document | Requirement Gathering | Good to Have | Priority & Trade-offs | Check whether NFRs are prioritised and any trade-off between competing ones is explained
Non-Functional Requirements (NFR) Document | Requirement Gathering | Good to Have | NFR Ownership | Check whether each NFR area has a named owner and approver
Technical Design Document | Design | Must Have | Architecture & Rationale | Verify whether the document explains not only the architecture but why that approach was chosen
Technical Design Document | Design | Must Have | Source Extract Design | Verify whether each source names its connection method, extraction strategy and how incremental data is identified
Technical Design Document | Design | Must Have | Schema & Grain Design | Verify whether the target schema, keys, grain, relationships and slowly changing dimension handling are documented
Technical Design Document | Design | Must Have | Transformation Design | Verify whether the transformation layers and the way business rules are implemented are specified
Technical Design Document | Design | Must Have | Orchestration & Dependencies | Verify whether job orchestration, schedules, dependencies and failure behaviour are defined
Technical Design Document | Design | Must Have | Reporting Layer Design | Verify whether dataset design, connection mode, measure standards and report performance approach are documented
Technical Design Document | Design | Must Have | Error Handling & Reconciliation | Verify whether error handling, retry logic, audit tables and source-to-target reconciliation are designed
Technical Design Document | Design | Must Have | Performance Design | Verify whether partitioning, indexing, incremental processing and growth headroom are addressed
Technical Design Document | Design | Must Have | Naming Standards | Verify whether naming conventions for objects, jobs, models and code artefacts are defined
Technical Design Document | Design | Must Have | Environment & CI/CD Design | Verify whether environment topology, branching, code promotion and deployment automation are documented
Technical Design Document | Design | Must Have | Design Approved Before Build | Verify whether architecture and client approval were obtained before development started
Technical Design Document | Design | Must Have | End-to-End Components | Verify whether the diagram shows everything from source systems through to consumption
Technical Design Document | Design | Must Have | Layer Separation | Verify whether the raw, cleansed and curated layers are drawn as distinct zones
Technical Design Document | Design | Must Have | Environment Boundaries | Verify whether development, test and production environments and their boundaries are visible
Technical Design Document | Design | Must Have | Flow Direction & Protocol | Verify whether connections show the direction of flow and how the interaction happens
Technical Design Document | Design | Must Have | Security Components | Verify whether the identity provider, secret store, network boundaries and access control points are drawn
Technical Design Document | Design | Must Have | Platform Labelling | Verify whether each component is labelled with the actual platform or service in use
Technical Design Document | Design | Must Have | Consumers & Outbound Feeds | Verify whether reporting layers, downstream consumers and outbound feeds are represented
Technical Design Document | Design | Must Have | Legend & Readability | Verify whether a legend explains the notation and the labelling is legible
Technical Design Document | Design | Must Have | Entities & Relationships | Verify whether entities, attributes and relationships are defined with cardinality marked
Technical Design Document | Design | Must Have | Logical & Physical Models | Verify whether both a logical and a physical model exist and agree with each other
Technical Design Document | Design | Must Have | Keys & Constraints | Verify whether primary keys, foreign keys, unique constraints and indexes are specified
Technical Design Document | Design | Must Have | Fact Grain Defined | Verify whether the grain of each fact table is stated and shared dimensions are conformed
Technical Design Document | Design | Must Have | Types & Naming Standards | Verify whether data types, lengths and object naming follow the agreed standard
Technical Design Document | Design | Must Have | Historisation Approach | Verify whether the historisation approach is specified for each entity that changes over time
Technical Design Document | Design | Good to Have | Alternatives Considered | Check whether alternatives were considered and the reason for the chosen option is recorded
Technical Design Document | Design | Good to Have | Infrastructure Sizing | Check whether environment configuration, compute sizing and running cost are documented
Technical Design Document | Design | Good to Have | Orchestration & CI/CD | Check whether orchestration, scheduling and deployment pipelines are depicted
Technical Design Document | Design | Good to Have | Monitoring Components | Check whether monitoring, logging and alerting components appear on the diagram
Technical Design Document | Design | Good to Have | HA & DR Representation | Check whether redundancy, failover or disaster recovery components are shown
Technical Design Document | Design | Good to Have | Matches Deployed Schema | Check whether the model matches the schema actually deployed, including post-approval changes
Technical Design Document | Design | Good to Have | Volumetrics per Entity | Check whether expected row counts and growth are documented per entity
Integration Design | Design | Must Have | Interface Inventory | Verify whether every inbound and outbound interface is inventoried with an ID and description
Integration Design | Design | Must Have | Source & Target Objects | Verify whether each interface names its source system, source object, target system and target object
Integration Design | Design | Must Have | Pattern & Load Type | Verify whether each interface states its pattern, such as batch, incremental, full load or API
Integration Design | Design | Must Have | Trigger & Schedule | Verify whether triggers, schedules, refresh frequency and expected volumes are documented
Integration Design | Design | Must Have | Field-level Mapping | Verify whether mapping is specified at field level with data types, nullability and transformation rules
Integration Design | Design | Must Have | File & API Contract | Verify whether file formats, delimiters, naming patterns and API contracts are specified
Integration Design | Design | Must Have | Error Handling & Retry | Verify whether each interface defines its error scenarios, retry logic and alert routing
Integration Design | Design | Must Have | Reconciliation Controls | Verify whether row counts and reconciliation checkpoints between source and target are defined
Integration Design | Design | Must Have | Interface Ownership | Verify whether interface owners, upstream dependencies and third-party responsibilities are identified
Integration Design | Design | Good to Have | Latency & Processing Window | Check whether expected latency and processing windows are quantified
Integration Design | Design | Good to Have | Interface Build Status | Check whether build and test status is tracked per interface
Data Flow Diagram | Design | Must Have | Source to Consumption | Verify whether the diagram traces data from every source through to final consumption
Data Flow Diagram | Design | Must Have | Processing Stages | Verify whether each processing stage and the transitions between layers are represented
Data Flow Diagram | Design | Must Have | Dataset Labelling | Verify whether objects at each stage are named rather than shown as generic boxes
Data Flow Diagram | Design | Must Have | Direction & Frequency | Verify whether each flow shows its direction and how often it runs
Data Flow Diagram | Design | Must Have | Rule Application Points | Verify whether the points where transformations or business rules apply are identified
Data Flow Diagram | Design | Must Have | Downstream Consumers | Verify whether outbound extracts, downstream systems and report consumers appear on the diagram
Data Flow Diagram | Design | Good to Have | DQ Checkpoints Shown | Check whether data quality and validation checkpoints are marked within the flow
Data Flow Diagram | Design | Good to Have | Overview & Detail Views | Check whether both an overview and a detailed view are provided
Wireframes / Figma for Dashboard | Design | Must Have | All Screens Covered | Verify whether a wireframe exists for every dashboard, screen and navigation page in scope
Wireframes / Figma for Dashboard | Design | Must Have | KPI & Visual Placement | Verify whether each KPI and chart is placed on the layout with its intended visual type
Wireframes / Figma for Dashboard | Design | Must Have | Filters & Navigation | Verify whether filters, default selections, drill paths and navigation controls are shown
Wireframes / Figma for Dashboard | Design | Must Have | Layout & Canvas Spec | Verify whether canvas size, grid alignment and spacing are specified
Wireframes / Figma for Dashboard | Design | Must Have | Interaction Behaviour | Verify whether cross-filtering, drill-through, tooltip and bookmark behaviour is described
Wireframes / Figma for Dashboard | Design | Must Have | Traceable to KPIs | Verify whether each visual maps to an approved requirement or KPI definition
Wireframes / Figma for Dashboard | Design | Must Have | Client Sign-off Before Build | Verify whether business stakeholders approved the wireframes before development began
Wireframes / Figma for Dashboard | Design | Good to Have | Style Guide Adherence | Check whether fonts, colour palette and component styling follow the agreed style guide
Wireframes / Figma for Dashboard | Design | Good to Have | Readability & Accessibility | Check whether readability, colour contrast and usability have been considered
Wireframes / Figma for Dashboard | Design | Good to Have | Empty & Error States | Check whether no-data, loading and error states are depicted
Wireframes / Figma for Dashboard | Design | Good to Have | Wireframe Versions | Check whether wireframe versions and feedback rounds are tracked
Source to Target Mapping (STTM) | Design | Must Have | Every Target Field Mapped | Verify whether every target field has a source field or an explicitly stated derivation
Source to Target Mapping (STTM) | Design | Must Have | Source & Target Named | Verify whether each mapping names its source system, source object, target schema and target table
Source to Target Mapping (STTM) | Design | Must Have | Types & Conversion Rules | Verify whether data types and lengths on both sides are stated along with any conversion rule
Source to Target Mapping (STTM) | Design | Must Have | Derivation Logic | Verify whether derived fields carry the actual rule rather than a description of it
Source to Target Mapping (STTM) | Design | Must Have | Keys, Grain & Joins | Verify whether business keys, join conditions and record grain are defined
Source to Target Mapping (STTM) | Design | Must Have | Null & Default Handling | Verify whether nullability, default values and handling of invalid data are specified
Source to Target Mapping (STTM) | Design | Must Have | Load Type & History | Verify whether load type, incremental keys, deduplication and historisation treatment are specified
Source to Target Mapping (STTM) | Design | Must Have | Filters & Delete Handling | Verify whether record filters, exclusions and delete handling are documented
Source to Target Mapping (STTM) | Design | Good to Have | Traceable to Requirements | Check whether mappings tie back to requirement or business rule identifiers
Source to Target Mapping (STTM) | Design | Good to Have | Points to a Data Model | Check whether the mapping references an approved physical data model rather than standing in for one
Unit Testing Document | Development | Must Have | Component Coverage | Verify whether every built component has at least one test, including extracts, transformations, measures and security roles
Unit Testing Document | Development | Must Have | Test ID & Description | Verify whether each test carries an ID, the module under test and what it validates
Unit Testing Document | Development | Must Have | Expected Result Stated | Verify whether a precise expected result was stated for each test
Unit Testing Document | Development | Must Have | Inputs & Pre-conditions | Verify whether inputs, pre-conditions and test data are documented well enough to re-run the test
Unit Testing Document | Development | Must Have | Actual Result & Status | Verify whether actual results and pass or fail status are recorded for every test
Unit Testing Document | Development | Must Have | Negative & Boundary Cases | Verify whether nulls, duplicates, invalid inputs and boundary values were tested alongside the clean cases
Unit Testing Document | Development | Must Have | Execution Evidence | Verify whether tester name, execution date and supporting evidence such as query output are captured
Unit Testing Document | Development | Must Have | Defect Link & Retest | Verify whether failed tests link to a defect and show a retest result after the fix
Unit Testing Document | Development | Must Have | Signed Off Before SIT | Verify whether unit testing was signed off before the build was handed to system testing
Unit Testing Document | Development | Good to Have | Repeatable Tests | Check whether tests are automated or scripted so they can be re-run on demand
Unit Testing Document | Development | Good to Have | Coverage by Module | Check whether coverage or completeness is reported by module or layer
Unit Testing Document | Development | Good to Have | Pass Rate Summary | Check whether an aggregated pass rate is available
Defect Log/Incident Tracker | Testing | Must Have | Defect Description | Verify whether each defect states what was observed against what was expected
Defect Log/Incident Tracker | Testing | Must Have | Steps to Reproduce | Verify whether steps to reproduce, environment, build version and evidence are captured
Defect Log/Incident Tracker | Testing | Must Have | Severity & Priority | Verify whether severity and priority are assigned using defined criteria rather than judgement in the moment
Defect Log/Incident Tracker | Testing | Must Have | Module & Test Case Link | Verify whether each defect links to the affected module, the test case that found it and the testing phase
Defect Log/Incident Tracker | Testing | Must Have | Raised By & Assigned To | Verify whether raised-by and assigned-to are recorded
Defect Log/Incident Tracker | Testing | Must Have | Root Cause Recorded | Verify whether resolved defects record the root cause and not only the fix applied
Defect Log/Incident Tracker | Testing | Must Have | Fix Build & Retest | Verify whether resolution details, fix build, retest outcome and closure date are recorded
Defect Log/Incident Tracker | Testing | Must Have | Status Discipline | Verify whether statuses follow a defined lifecycle with nothing left stale or ambiguous
Defect Log/Incident Tracker | Testing | Good to Have | Defect Ageing | Check whether defect ageing is tracked against the agreed resolution times
Defect Log/Incident Tracker | Testing | Good to Have | Defect Trend Analysis | Check whether defects are grouped by type and analysed for recurring patterns
Defect Log/Incident Tracker | Testing | Good to Have | Defect Leakage | Check whether defects found late or after go-live are traced back to the phase that should have caught them
Defect Log/Incident Tracker | Testing | Good to Have | Defect Summary View | Check whether a summary by severity, status and module is available
UAT Test Case Document / Expected Results | UAT | Must Have | Business Scenario Coverage | Verify whether scenarios cover every critical business process, KPI, report and user journey in scope
UAT Test Case Document / Expected Results | UAT | Must Have | Written in Business Language | Verify whether scenarios are written the way a business user works rather than as technical steps
UAT Test Case Document / Expected Results | UAT | Must Have | Pre-conditions & Role | Verify whether pre-conditions, user role, access setup and data period are specified
UAT Test Case Document / Expected Results | UAT | Must Have | Step-by-step Instructions | Verify whether the steps are numbered and clear enough for a business user to run unaided
UAT Test Case Document / Expected Results | UAT | Must Have | Acceptance Criteria | Verify whether each scenario says precisely what a pass looks like
UAT Test Case Document / Expected Results | UAT | Must Have | Expected vs Actual | Verify whether expected results, actual results and status are recorded per scenario
UAT Test Case Document / Expected Results | UAT | Must Have | Access Scenarios Tested | Verify whether scenarios test that users see only the data their role permits
UAT Test Case Document / Expected Results | UAT | Must Have | Defect Link & Retest | Verify whether failed scenarios link to a defect and show a retest outcome
UAT Test Case Document / Expected Results | UAT | Must Have | Tester & Date | Verify whether the client tester's name and the execution date are captured
UAT Test Case Document / Expected Results | UAT | Good to Have | Grouped by Business Area | Check whether scenarios are grouped by business area, module or user role
UAT Test Case Document / Expected Results | UAT | Good to Have | Edge Scenarios | Check whether unusual or exception business scenarios are included
UAT Deck | UAT | Must Have | UAT Session Conducted | Verify whether the UAT walkthrough session was held, with the date and participants recorded
UAT Deck | UAT | Must Have | Entry Criteria Confirmed | Verify whether the deck confirms SIT completion, environment readiness and test data availability before UAT began
UAT Deck | UAT | Must Have | Demo & Walkthrough Coverage | Verify whether the deck evidences a walkthrough of every dashboard, report or module in scope
UAT Deck | UAT | Must Have | Defect Summary Presented | Verify whether open defects with their severity and status were presented to the business
UAT Deck | UAT | Must Have | Exit Criteria Defined | Verify whether the deck states the UAT exit criteria and the route to formal sign-off
UAT Deck | UAT | Must Have | UAT Scope & Period | Verify whether the register states what was tested, in which environment and over what data period
UAT Deck | UAT | Must Have | Execution Summary | Verify whether the register summarises scenarios executed, passed, failed and deferred
UAT Deck | UAT | Must Have | Open Defects at Sign-off | Verify whether every defect still open at sign-off is listed with its severity and agreed disposition
UAT Deck | UAT | Must Have | Deferred Items Agreed | Verify whether deferred items carry an owner, a target release and explicit business acceptance
UAT Deck | UAT | Must Have | Approver Authority | Verify whether the person signing holds the authority to accept on behalf of the business
UAT Deck | UAT | Must Have | Written Sign-off | Verify whether sign-off is documented with name, role and date
UAT Deck | UAT | Must Have | Conditions of Acceptance | Verify whether any conditions attached to the acceptance are stated
UAT Deck | UAT | Must Have | Go-live Readiness | Verify whether the register confirms readiness to proceed to deployment
UAT Deck | UAT | Good to Have | Training & Enablement Covered | Check whether user training, navigation guidance or enablement material is included
UAT Deck | UAT | Good to Have | Feedback & Follow-up Actions | Check whether business feedback raised during UAT is listed with owners and target dates
UAT Deck | UAT | Good to Have | Sign-off by Business Area | Check whether sign-off is recorded separately for each business area or module
UAT Deck | UAT | Good to Have | Residual Risk Accepted | Check whether residual risks accepted by the business are acknowledged
Project Closure Deck / RTM | All Phases | Must Have | Scope Delivered vs Committed | Verify whether the deck shows what was committed at the start against what was actually delivered, with any variance explained
Project Closure Deck / RTM | All Phases | Must Have | Deliverable Handover Status | Verify whether every deliverable is listed with its final status and confirmation that it has been handed over to the client
Project Closure Deck / RTM | All Phases | Must Have | Milestone & Timeline Summary | Verify whether planned against actual dates are shown for the key milestones, with reasons for any slippage
Project Closure Deck / RTM | All Phases | Must Have | Success Criteria Achievement | Verify whether the success criteria agreed at initiation are restated and evidenced as met, partially met or not met
Project Closure Deck / RTM | All Phases | Must Have | Open Items & Deferred Scope | Verify whether items still open or deferred at closure are listed with an owner, a target and explicit client agreement
Project Closure Deck / RTM | All Phases | Must Have | Defect Status at Closure | Verify whether outstanding defects are shown with severity and the agreed disposition for each
Project Closure Deck / RTM | All Phases | Must Have | Support Transition & Ownership | Verify whether the deck states who supports the solution after closure, from when, and how issues should be raised
Project Closure Deck / RTM | All Phases | Must Have | Formal Closure Sign-off | Verify whether the deck carries formal client acceptance of project closure with an approver name, role and date
Project Closure Deck / RTM | All Phases | Must Have | End-to-End Traceability | Verify whether a single requirement can be followed through design, build, test case and UAT to closure
Project Closure Deck / RTM | All Phases | Must Have | Requirement ID Discipline | Verify whether each requirement carries a unique ID used consistently across every downstream document
Project Closure Deck / RTM | All Phases | Must Have | Two-way Traceability | Verify whether every requirement maps to a test case and every test case maps back to a requirement
Project Closure Deck / RTM | All Phases | Must Have | Coverage Gaps Visible | Verify whether requirements with no design, build or test coverage stand out rather than blending in
Project Closure Deck / RTM | All Phases | Must Have | CRs Added to Matrix | Verify whether approved change requests are added to the matrix with the same traceability as original requirements
Project Closure Deck / RTM | All Phases | Must Have | Requirement Status Tracking | Verify whether each requirement is tracked through to accepted
Project Closure Deck / RTM | All Phases | Good to Have | Effort & Budget Summary | Check whether final effort and budget against plan are summarised for the client
Project Closure Deck / RTM | All Phases | Good to Have | Lessons Learned Shared | Check whether key lessons from the engagement are shared rather than kept internal
Project Closure Deck / RTM | All Phases | Good to Have | Client Feedback Captured | Check whether client feedback or a satisfaction input was requested and recorded at closure
Project Closure Deck / RTM | All Phases | Good to Have | Next Phase & Enhancement Outlook | Check whether known enhancements, Phase 2 scope or roadmap items are outlined
Project Closure Deck / RTM | All Phases | Good to Have | Priority Tagging | Check whether requirements are tagged by priority so critical coverage can be confirmed first
Project Closure Deck / RTM | All Phases | Good to Have | Descoped Items Visible | Check whether descoped or deferred requirements remain visible with the rationale and decision owner