## Individual Audit
AI DELIVERY AUDIT REPORT
Project | Audit Type | Document | Document Category | Project Phase | Evaluation Category | Evaluation Metric | Evaluation Pointer | Score | Finding | Evidence | Recommendation
DW Warehousing and MDM | STAR | SOW_for_Assertio_DW_MDM_Ops_2025_26-for_signature.docx (1).pdf | SOW (Statement of Work) |  | Must Have | Agreement, Effective Date & Contract Reference Clarity | Verify whether effective date, governing agreement, contract references, amendment clauses, and legal applicability are clearly defined | 4 | The SOW clearly references the governing Master Services Agreement, states the SOW commencement date, incorporates the Agreement by reference, and confirms legal integration. However, amendment/change-to-contract language specific to this SOW is limited beyond incorporation and termination references. | "This Statement of Work is issued under the Master Services Agreement dated as of September 12, 2025 (“Agreement”)..."; "The terms and conditions of the Agreement are hereby incorporated into this Statement of Work by reference."; "This SOW shall commence on October 13, 2025, and shall continue until December 31, 2026 (15 months)..."; "This SOW (and the Agreement) constitutes the entire agreement between the parties..." | Add explicit SOW amendment language, approval authority for modifications, governing law/jurisdiction reference if not solely in the MSA, and clarify whether the signed date or October 13, 2025 is the SOW Effective Date.
DW Warehousing and MDM | STAR | SOW_for_Assertio_DW_MDM_Ops_2025_26-for_signature.docx (1).pdf | SOW (Statement of Work) |  | Must Have | Project Objectives, Services & Scope Definition | Verify whether project objectives, operational expectations, services to be provided, and business scope are clearly documented | 5 | The document clearly defines the project purpose, scope areas, datasets, business analysis, infrastructure setup, data warehousing, and MDM objectives. | "This SOW captures the scope for data onboarding and data matching activities."; "Project: Assertio Commercial DW and MDM Setup"; "ProcDNA will establish and configure the complete cloud and analytics infrastructure required to support Assertio’s Data Warehouse and MDM program."; "ProcDNA will design and implement a Commercial Data Lake to serve as the foundation for Assertio’s enterprise data warehouse."; "MDM Activities" | Retain the current structure and add a short executive summary tying the business outcome to the technical scope for even stronger clarity.
DW Warehousing and MDM | STAR | SOW_for_Assertio_DW_MDM_Ops_2025_26-for_signature.docx (1).pdf | SOW (Statement of Work) |  | Must Have | Services to be Provided by Service Provider | Verify whether all operational, reporting, support, enhancement, refresh, QC, validation, and stakeholder support activities are clearly listed | 4 | Services are broadly and clearly listed across business analysis, infrastructure, DW, MDM, QC, reporting, and support. Operational and support items are present, though some recurring operational service details are summarized more in pricing tables than in service descriptions. | "Requirements gathering sessions with stakeholders"; "Validation of requirements with business users"; "Provisioning of Azure subscription and required services"; "CI/CD pipelines for code, configuration, and data model deployment"; "Define and enforce DQM rules (validations, reference data standardization, exception handling)"; "Knowledge transfer sessions with Assertio team"; "Quality Control Checklist"; "Quality Assurance Tests"; "Weekly Status Report"; "12x5 Support (1:30 AM–12:30 PM EST)"; "Minor System Enhancements" | Consolidate all ongoing operational services into a dedicated operations section with service frequency, ownership, response expectations, and output definitions.
DW Warehousing and MDM | STAR | SOW_for_Assertio_DW_MDM_Ops_2025_26-for_signature.docx (1).pdf | SOW (Statement of Work) |  | Must Have | In-Scope vs Out-of-Scope Coverage | Verify whether supported activities, exclusions, enhancement limitations, and operational boundaries are clearly separated | 3 | The SOW includes at least one explicit out-of-scope item and notes some operational/reporting exclusions, but overall separation of in-scope vs out-of-scope items is incomplete and not consistently structured across all workstreams. | "with the Reporting layer excluded from Project scope except existing reporting tables (sales and calls)."; "DW Deliverables... (Other Reporting Data Marts out of scope)"; "Out Of Scope • Assertio facilitates appropriate Third-Party data-sharing agreements between ProcDNA and Data Vendor" | Create a dedicated in-scope/out-of-scope matrix covering reporting, support, enhancements, third-party dependencies, production support boundaries, and data source additions.
DW Warehousing and MDM | STAR | SOW_for_Assertio_DW_MDM_Ops_2025_26-for_signature.docx (1).pdf | SOW (Statement of Work) |  | Must Have | Deliverables & Operational Expectations | Verify whether deliverables such as refreshed reports, extracts, QC checklists, validations, insights, and operational outputs are clearly defined | 5 | Deliverables are extensively documented for business analysis, infrastructure, DW, MDM, and operations, including plans, reports, documentation, testing outputs, and governance artifacts. | "Detailed Project Plan having delivery date, review completion date and approval date"; "Business Requirements Document"; "Business Process Flow Diagrams"; "Fully provisioned and configured Azure and Databricks environments"; "System and data architecture diagrams"; "Data quality management framework with monitoring and alerts"; "Databricks-Based MDM Tool"; "Monthly Status Reports"; "System Integration Testing (SIT) Reports"; "Quality Control Checklist"; "Quality Assurance Tests"; "SOPs and SLAs"; "Change Management Tracker"; "Backlog Tracker"; "Performance Reports & KPIs" | Add acceptance format, due dates, and owner-by-deliverable to make the deliverables operationally enforceable.
DW Warehousing and MDM | STAR | SOW_for_Assertio_DW_MDM_Ops_2025_26-for_signature.docx (1).pdf | SOW (Statement of Work) |  | Must Have | Timeline, Milestones & Duration Management | Verify whether project duration, completion dates, milestone expectations, refresh schedules, and operational timelines are documented | 4 | The SOW defines overall term, implementation duration, a visual timeline, weekly summaries, monthly reporting, daily MDM execution, and invoice dates. However, milestone completion criteria and exact phase exit dates are not fully textualized. | "This SOW shall commence on October 13, 2025, and shall continue until December 31, 2026 (15 months)"; "Project Plan: A detailed 10-week project plan outlining key activities, milestones, and deliverables on a week-by-week basis"; "Deployment of automated orchestration workflows to enable daily execution of MDM pipelines"; "weekly summaries of the progress"; "Monthly Status Reports"; "20 Weeks (5 months)"; "Implementation Timelines" | Add a milestone table with planned start/end dates, dependencies, milestone owners, and formal completion criteria for each phase.
DW Warehousing and MDM | STAR | SOW_for_Assertio_DW_MDM_Ops_2025_26-for_signature.docx (1).pdf | SOW (Statement of Work) |  | Must Have | Service Provider Contacts & Governance Structure | Verify whether project leaders, delivery managers, escalation contacts, invoicing contacts, and governance ownership are documented | 3 | Primary contacts and key delivery roles are listed, but escalation paths, governance cadence, steering structure, and invoicing contacts are not fully defined. | "Service Provider Contact(s): Ankush Kumar"; "Company Contact(s): Zander Poth"; "Project Delivery Manager: Hannan Ahmed Rizvi (Director, India)"; "Sampoorna Agrawal (Engagement Lead, India)" | Add a governance section with escalation matrix, meeting cadence, steering committee roles, invoicing contact, operational review forums, and issue resolution hierarchy.
DW Warehousing and MDM | STAR | SOW_for_Assertio_DW_MDM_Ops_2025_26-for_signature.docx (1).pdf | SOW (Statement of Work) |  | Must Have | Team Structure & Resource Allocation | Verify whether delivery hierarchy, team structure, operational ownership, and resource responsibilities are clearly defined | 4 | The team composition and named roles are documented, but responsibilities per role and capacity/allocation percentages are not specified. | "4) Staffing ProcDNA will staff the following team on this project– Project Delivery Manager: Hannan Ahmed Rizvi (Director, India)"; "Implementation: • Sampoorna Agrawal (Engagement Lead, India) • Raghav Gupta (Associate Engagement Lead, India) • Mayank Jain (Project Lead, India) • Raghav Bansal (Technology Analyst, India) • Arshia Dhiman (Technology Analyst, India) • TBD (Senior Cloud Engineer, India)" | Add a RACI or resource plan showing role responsibilities, expected effort, backup coverage, and whether resources are dedicated, shared, or TBD.
DW Warehousing and MDM | STAR | SOW_for_Assertio_DW_MDM_Ops_2025_26-for_signature.docx (1).pdf | SOW (Statement of Work) |  | Must Have | Roles, Responsibilities & Operational Ownership | Verify whether client/vendor responsibilities, operational ownership, dependency handling, and support responsibilities are clearly assigned | 3 | Vendor responsibilities are well described, and one client responsibility is explicitly identified. However, broader client/vendor operational ownership, dependency management, and support boundaries are not comprehensively assigned. | "ProcDNA will be responsible for end-to-end setup"; "Service Provider shall promptly provide Company with weekly summaries"; "Assertio facilitates appropriate Third-Party data-sharing agreements between ProcDNA and Data Vendor" | Add a responsibilities matrix covering ProcDNA, Assertio, and third parties for data access, approvals, UAT, issue resolution, production support, and change handling.
DW Warehousing and MDM | STAR | SOW_for_Assertio_DW_MDM_Ops_2025_26-for_signature.docx (1).pdf | SOW (Statement of Work) |  | Must Have | Compensation, Cost, Pricing & Billing Rate Structure | Verify whether pricing structure, blended billing rates, enhancement rates, compensation limits, pass-through costs, and commercial expectations are clearly documented | 4 | The SOW clearly states total compensation, component costs, and cost categories, including a cap and estimated cloud costs. However, billing rates/blended rates and enhancement rate logic are not defined. | "Company agrees to pay Service Provider on the following basis: $550,000."; "Any amount in excess of the Maximum Amount requires the Company’s prior written approval."; "Data Warehouse Implementation $185,000"; "Custom MDM Implementation for HCOs $100,000"; "Miscellaneous Expenses (Travel, etc.) $10,000 (not more than 5%)"; "IT Infra Setup and Management Cost... $30,000"; "Operations Cost... $125,000"; "Cloud Application Infra Cost (Mar 2026- Dec 2026) (Estimate) $100,000" | Add rate-card detail for personnel, enhancement/change billing rates, assumptions behind cloud estimates, and treatment of overages/unused budget.
DW Warehousing and MDM | STAR | SOW_for_Assertio_DW_MDM_Ops_2025_26-for_signature.docx (1).pdf | SOW (Statement of Work) |  | Must Have | Invoicing Schedule & Payment Milestones | Verify whether invoicing frequency, payment milestones, invoice conditions, billing cycles, and milestone-based payment schedules are documented | 4 | The SOW includes a detailed monthly invoicing schedule and references a final reconciliation invoice, but payment terms, due dates after invoice receipt, and invoice acceptance conditions are absent. | "Payments will be made according to the payment schedule in the attached Attachment A."; "Upon notification by the Company that the Services have been completed, Service Provider will prepare a final Project reconciliations invoice"; "6) Invoicing Schedule New Invoicing Schedule -"; "10th October 2025 $19,000" ... "10th December 2026 $44,000" | Add net payment terms, invoice submission requirements, tax treatment, dispute process, and whether invoices are milestone-based, time-based, or fixed monthly installments.
DW Warehousing and MDM | STAR | SOW_for_Assertio_DW_MDM_Ops_2025_26-for_signature.docx (1).pdf | SOW (Statement of Work) |  | Must Have | Travel, Reimbursement & Pass-through Cost Governance | Verify whether travel clauses, reimbursement handling, pass-through approval conditions, and additional cost governance are documented | 3 | Travel and cloud costs are identified commercially, and excess amounts require prior approval at the overall amount level, but reimbursement process and pass-through governance are not fully defined. | "Miscellaneous Expenses (Travel, etc.) $10,000 (not more than 5%)"; "Cloud Application Infra Cost (Mar 2026- Dec 2026) (Estimate) $100,000"; "Any amount in excess of the Maximum Amount requires the Company’s prior written approval." | Define reimbursable expense categories, pre-approval thresholds, documentation requirements, billing treatment for pass-through costs, and ownership of direct cloud vendor charges.
DW Warehousing and MDM | STAR | SOW_for_Assertio_DW_MDM_Ops_2025_26-for_signature.docx (1).pdf | SOW (Statement of Work) |  | Must Have | Change Management & Enhancement Governance | Verify whether change requests, enhancement limits, additional billing conditions, and scope revision handling are documented | 2 | The SOW mentions change management artifacts and minor enhancements, but it does not define a formal change request process, approval workflow, scope revision mechanism, or pricing treatment for changes. | "Change Management Tracker"; "Minor System Enhancements"; "Any amount in excess of the Maximum Amount requires the Company’s prior written approval." | Add a formal change control clause covering request intake, impact assessment, approval authority, turnaround times, scope baseline, and commercial implications of enhancements.
DW Warehousing and MDM | STAR | SOW_for_Assertio_DW_MDM_Ops_2025_26-for_signature.docx (1).pdf | SOW (Statement of Work) |  | Must Have | Acceptance Criteria & Sign-off Readiness | Verify whether milestone completion criteria, acceptance expectations, approval workflows, and sign-off conditions are documented | 2 | Some deliverables refer to approval dates and stewardship sign-off, but the SOW lacks formal acceptance criteria, review periods, rejection/remediation steps, and sign-off workflow by deliverable. | "Detailed Project Plan having delivery date, review completion date and approval date"; "Stewardship workflows & sign-off"; "Upon notification by the Company that the Services have been completed" | Define deliverable acceptance criteria, client review windows, deemed acceptance rules, remediation obligations, and authorized signatories for milestone sign-off.
DW Warehousing and MDM | STAR | SOW_for_Assertio_DW_MDM_Ops_2025_26-for_signature.docx (1).pdf | SOW (Statement of Work) |  | Must Have | Operational Support, SLA & Service Expectations | Verify whether dashboard refresh support, discrepancy handling, stakeholder query support, QC expectations, and operational SLAs are clearly defined | 3 | The SOW includes support coverage, QC/QA deliverables, monitoring, alerts, and SLAs as outputs, but measurable SLA targets and support procedures are not clearly defined. | "12x5 Support (1:30 AM–12:30 PM EST)"; "Quality Control Checklist"; "Quality Assurance Tests"; "SOPs and SLAs"; "Data quality management framework with monitoring and alerts"; "Monthly Status Reports: Structured reports providing monthly progress updates, identified risks, and mitigation actions" | Specify incident severity levels, response/resolution SLAs, support channels, stakeholder query handling, discrepancy management procedures, and service exclusions.
DW Warehousing and MDM | STAR | SOW_for_Assertio_DW_MDM_Ops_2025_26-for_signature.docx (1).pdf | SOW (Statement of Work) |  | Must Have | Risk, Dependency & Assumption Management | Verify whether assumptions, operational constraints, dependency handling, and risk conditions are documented | 3 | Risks and dependencies are partially addressed through status reports, RAID logs, and one explicit client dependency, but assumptions and constraints are not comprehensively documented. | "Monthly Status Reports: Structured reports providing monthly progress updates, identified risks, and mitigation actions"; "RAID logs"; "Assertio facilitates appropriate Third-Party data-sharing agreements between ProcDNA and Data Vendor" | Add a formal assumptions/dependencies/constraints section, including data availability, stakeholder responsiveness, infrastructure access, third-party access, and schedule-impact conditions.
DW Warehousing and MDM | STAR | SOW_for_Assertio_DW_MDM_Ops_2025_26-for_signature.docx (1).pdf | SOW (Statement of Work) |  | Good to Have | Strategic Context & Business Alignment | Verify whether strategic objectives, business alignment, and transformation goals are documented | 3 | The document implies strategic intent around enterprise DW/MDM enablement and reporting support, but business transformation goals and expected business outcomes are not explicitly articulated. | "support Assertio’s Data Warehouse and MDM program"; "serve as the foundation for Assertio’s enterprise data warehouse"; "support Assertio’s existing reporting requirements" | Add a business context section summarizing why the program matters, expected business value, and how success aligns to Assertio’s commercial data strategy.
DW Warehousing and MDM | STAR | SOW_for_Assertio_DW_MDM_Ops_2025_26-for_signature.docx (1).pdf | SOW (Statement of Work) |  | Good to Have | Versioning, Documentation & Audit Governance | Verify whether revision logs, version tracking, documentation governance, and audit traceability are maintained | 2 | The SOW contains documentation deliverables and audit logging references for the technical solution, but document version control and revision governance for the SOW itself are not shown. | "Audit logging and activity monitoring"; "System and data architecture diagrams"; "System/Requirement Documentation"; "Requirements Traceability Matrix" | Add document version number, revision history, approval log, and document control owner for audit traceability.
DW Warehousing and MDM | STAR | SOW_for_Assertio_DW_MDM_Ops_2025_26-for_signature.docx (1).pdf | SOW (Statement of Work) |  | Good to Have | Scope Visualization & Workflow Representation | Verify whether workflow diagrams, operational flows, and scope representations are visually documented | 5 | The SOW includes clear visual representations of the commercial data flow, MDM process, and implementation timeline. | "Commercial data flow diagram"; "MDM"; "Implementation Timelines"; "Business Process Flow Diagrams" | Retain the visual aids and consider adding a legend and explicit in-scope/out-of-scope annotations within diagrams.
DW Warehousing and MDM | STAR | SOW_for_Assertio_DW_MDM_Ops_2025_26-for_signature.docx (1).pdf | SOW (Statement of Work) |  | Good to Have | Future Enhancement & Scalability Planning | Verify whether future enhancements, scalability expectations, and operational growth planning are documented | 4 | The SOW addresses scalability in the platform design and references future data sources and minor enhancements, but a structured roadmap for future phases is not provided. | "enabling scalable data models and reporting"; "Support ad-hoc ingestion for datasets such as OneKey or additional rosters"; "Etc. (data sources which are part of the current Medidata Implementation but not present in the list above)"; "Minor System Enhancements" | Add a future-state roadmap for additional reporting marts, new source onboarding, scaling assumptions, and transition from minor to major enhancements.
DW Warehousing and MDM | STAR | SOW_for_Assertio_DW_MDM_Ops_2025_26-for_signature.docx (1).pdf | SOW (Statement of Work) |  | Good to Have | Compliance, Confidentiality & Legal Governance | Verify whether confidentiality clauses, compliance obligations, IP ownership, and legal governance expectations are documented | 3 | Compliance and legal governance are partially covered through incorporation of the MSA and references to security/compliance controls, but confidentiality, IP ownership, and legal obligations are not restated in the SOW. | "The terms and conditions of the Agreement are hereby incorporated into this Statement of Work by reference."; "ensuring enterprise-grade security and compliance"; "Identity and access management with role-based permissions"; "Audit logging and activity monitoring" | Reference the specific MSA sections covering confidentiality, IP, data protection, and compliance, or summarize their applicability in the SOW for clarity.

## Combined Summary
AI AUDIT EXECUTIVE SUMMARY
Project Details
Project Name | DW Warehousing and MDM
Audit Type | STAR
Generated Timestamp | 2026-07-28 13:40:14
Documents Audited
Cross Document Findings
None
Gaps & Risks
• | Gap : The SOW includes at least one explicit out-of-scope item and notes some operational/reporting exclusions, but overall separation of in-scope vs out-of-scope items is incomplete and not consistently structured across all workstreams. Impact : See individual audit for details. Documents : SOW_for_Assertio_DW_MDM_Ops_2025_26-for_signature.docx (1).pdf
• | Gap : Primary contacts and key delivery roles are listed, but escalation paths, governance cadence, steering structure, and invoicing contacts are not fully defined. Impact : See individual audit for details. Documents : SOW_for_Assertio_DW_MDM_Ops_2025_26-for_signature.docx (1).pdf
• | Gap : Vendor responsibilities are well described, and one client responsibility is explicitly identified. However, broader client/vendor operational ownership, dependency management, and support boundaries are not comprehensively assigned. Impact : See individual audit for details. Documents : SOW_for_Assertio_DW_MDM_Ops_2025_26-for_signature.docx (1).pdf
• | Gap : Travel and cloud costs are identified commercially, and excess amounts require prior approval at the overall amount level, but reimbursement process and pass-through governance are not fully defined. Impact : See individual audit for details. Documents : SOW_for_Assertio_DW_MDM_Ops_2025_26-for_signature.docx (1).pdf
• | Gap : The SOW mentions change management artifacts and minor enhancements, but it does not define a formal change request process, approval workflow, scope revision mechanism, or pricing treatment for changes. Impact : See individual audit for details. Documents : SOW_for_Assertio_DW_MDM_Ops_2025_26-for_signature.docx (1).pdf
• | Gap : Some deliverables refer to approval dates and stewardship sign-off, but the SOW lacks formal acceptance criteria, review periods, rejection/remediation steps, and sign-off workflow by deliverable. Impact : See individual audit for details. Documents : SOW_for_Assertio_DW_MDM_Ops_2025_26-for_signature.docx (1).pdf
• | Gap : The SOW includes support coverage, QC/QA deliverables, monitoring, alerts, and SLAs as outputs, but measurable SLA targets and support procedures are not clearly defined. Impact : See individual audit for details. Documents : SOW_for_Assertio_DW_MDM_Ops_2025_26-for_signature.docx (1).pdf
• | Gap : Risks and dependencies are partially addressed through status reports, RAID logs, and one explicit client dependency, but assumptions and constraints are not comprehensively documented. Impact : See individual audit for details. Documents : SOW_for_Assertio_DW_MDM_Ops_2025_26-for_signature.docx (1).pdf
• | Gap : The document implies strategic intent around enterprise DW/MDM enablement and reporting support, but business transformation goals and expected business outcomes are not explicitly articulated. Impact : See individual audit for details. Documents : SOW_for_Assertio_DW_MDM_Ops_2025_26-for_signature.docx (1).pdf
• | Gap : The SOW contains documentation deliverables and audit logging references for the technical solution, but document version control and revision governance for the SOW itself are not shown. Impact : See individual audit for details. Documents : SOW_for_Assertio_DW_MDM_Ops_2025_26-for_signature.docx (1).pdf
• | Gap : Compliance and legal governance are partially covered through incorporation of the MSA and references to security/compliance controls, but confidentiality, IP ownership, and legal obligations are not restated in the SOW. Impact : See individual audit for details. Documents : SOW_for_Assertio_DW_MDM_Ops_2025_26-for_signature.docx (1).pdf
Strengths
• | [Agreement, Effective Date & Contract Reference Clarity] The SOW clearly references the governing Master Services Agreement, states the SOW commencement date, incorporates the Agreement by reference, and confirms legal integration. However, amendment/change-to-contract language specific to this SOW is limited beyond incorporation and termination references.
• | [Project Objectives, Services & Scope Definition] The document clearly defines the project purpose, scope areas, datasets, business analysis, infrastructure setup, data warehousing, and MDM objectives.
• | [Services to be Provided by Service Provider] Services are broadly and clearly listed across business analysis, infrastructure, DW, MDM, QC, reporting, and support. Operational and support items are present, though some recurring operational service details are summarized more in pricing tables than in service descriptions.
• | [Deliverables & Operational Expectations] Deliverables are extensively documented for business analysis, infrastructure, DW, MDM, and operations, including plans, reports, documentation, testing outputs, and governance artifacts.
• | [Timeline, Milestones & Duration Management] The SOW defines overall term, implementation duration, a visual timeline, weekly summaries, monthly reporting, daily MDM execution, and invoice dates. However, milestone completion criteria and exact phase exit dates are not fully textualized.
• | [Team Structure & Resource Allocation] The team composition and named roles are documented, but responsibilities per role and capacity/allocation percentages are not specified.
• | [Compensation, Cost, Pricing & Billing Rate Structure] The SOW clearly states total compensation, component costs, and cost categories, including a cap and estimated cloud costs. However, billing rates/blended rates and enhancement rate logic are not defined.
• | [Invoicing Schedule & Payment Milestones] The SOW includes a detailed monthly invoicing schedule and references a final reconciliation invoice, but payment terms, due dates after invoice receipt, and invoice acceptance conditions are absent.
• | [Scope Visualization & Workflow Representation] The SOW includes clear visual representations of the commercial data flow, MDM process, and implementation timeline.
• | [Future Enhancement & Scalability Planning] The SOW addresses scalability in the platform design and references future data sources and minor enhancements, but a structured roadmap for future phases is not provided.
Recommendations
• | Recommendation : Add a formal change control clause covering request intake, impact assessment, approval authority, turnaround times, scope baseline, and commercial implications of enhancements. Priority : medium Documents : SOW_for_Assertio_DW_MDM_Ops_2025_26-for_signature.docx (1).pdf
• | Recommendation : Define deliverable acceptance criteria, client review windows, deemed acceptance rules, remediation obligations, and authorized signatories for milestone sign-off. Priority : medium Documents : SOW_for_Assertio_DW_MDM_Ops_2025_26-for_signature.docx (1).pdf
• | Recommendation : Add document version number, revision history, approval log, and document control owner for audit traceability. Priority : medium Documents : SOW_for_Assertio_DW_MDM_Ops_2025_26-for_signature.docx (1).pdf